## Gantt Chart (Aug - Mar)
|  |  |  | Aug 2025 | Sep 2025 | Oct 2025 | Nov 2025 | Dec 2025 | Jan 2026 | Feb 2026 | Mar 2026
Task Name | Duration | Start | Finish
Technical Recruiter Platform | 232 days | Fri 01-08-25 | Fri 20-03-26
Requirement Gathering | 20 days | Fri 01-08-25 | Wed 20-08-25
Planning | 21 days | Thu 21-08-25 | Wed 10-09-25
Analysis and Design | 20 days | Thu 11-09-25 | Tue 30-09-25
Module 1: Registration & Auth | 1 mon | Wed 01-10-25 | Fri 31-10-25
Planning | 5 days | Wed 01-10-25 | Sun 05-10-25
Analysis and Design | 5 days | Mon 06-10-25 | Fri 10-10-25
Coding | 15 days | Sat 11-10-25 | Sat 25-10-25
Testing | 6 days | Sun 26-10-25 | Fri 31-10-25
Module 2: Job Descriptions | 1 mon | Sat 01-11-25 | Sun 30-11-25
Planning | 5 days | Sat 01-11-25 | Wed 05-11-25
Analysis and Design | 5 days | Thu 06-11-25 | Mon 10-11-25
Coding | 15 days | Tue 11-11-25 | Tue 25-11-25
Testing | 5 days | Wed 26-11-25 | Sun 30-11-25
Module 3: AI Resume Parsing | 1.8 mons | Mon 01-12-25 | Sun 25-01-26
Planning | 10 days | Mon 01-12-25 | Wed 10-12-25
Analysis and Design | 10 days | Thu 11-12-25 | Sat 20-12-25
Coding | 26 days | Sun 21-12-25 | Thu 15-01-26
Testing | 10 days | Fri 16-01-26 | Sun 25-01-26
Module 4: Interview Room | 1.5 mons | Mon 26-01-26 | Thu 12-03-26
Planning | 11 days | Mon 26-01-26 | Thu 05-02-26
Analysis and Design | 10 days | Fri 06-02-26 | Sun 15-02-26
Coding | 18 days | Mon 16-02-26 | Thu 05-03-26
Testing | 7 days | Fri 06-03-26 | Thu 12-03-26
Final Integration & Deployment | 8 days | Fri 13-03-26 | Fri 20-03-26
System Testing | 4 days | Fri 13-03-26 | Mon 16-03-26
Bug Fixing | 2 days | Tue 17-03-26 | Wed 18-03-26
Deployment & Report | 2 days | Thu 19-03-26 | Fri 20-03-26